## Product Backlog
ID | Importance Weight | Story | Notes | Naglis | Aleksandar | Michael | Nikita
0.0.1 | 50 | We need somewhere we can communicate, record our sprints, and SCRUM. Make a Trello board and a Discord group. | Naglis created a Trello board and Discord server | Scrum Master | Developer | Team Member | Product Manager | Presentation: https://drive.google.com/file/d/1PW-koTggizikCsR54HuU4z9VZbvWWn4h/view
0.0.2 | 20 | We need to share our code and get the ball rolling | Michael created a Github repo, added the team, and explained how to checkout branches and merge | Developer | Developer | Scrum Master | Product Manager | Demo: https://drive.google.com/file/d/1v0RqENJzIZW6eY_uGi0Ub65oZkaQP-2q/view
0.1.0 | 15 | To learn React Native, we should experiment with the boilerplates and explore the prebuilts | Aleksandar created a React Native application to demo | Scrum Master | Developer | Developer | Product Manager | GitHub: https://github.com/DeveloperBlue/Algorithm-Visualizer
0.1.1 | 50 | It is best to plan our application layout beforehand, so we can make sure the UI is functional and also looks good | Aleksandar created a wireframe of the UI | Developer | Developer | Scrum Master | Product Manager
0.1.2 | 20 | Research required, how to handle animations in React Native | Aleksandar and Naglis explored React Native animation libraries | Developer | Developer | Scrum Master | Product Manager
0.1.2b | 20 | Research required on how to handle animations in React Native | Naglis, Michael, and Nikita explored Javascript animation libraries | Developer | Scrum Master | Developer | Developer
0.1.3 | 50 | Expectations and limitations should be set and declared so the team has an understanding of what the final product should look like | Naglis added color-coded labels to the Trello board to categorize cards. Michael pitched the idea for multi-gridded support and dynamic datasets from an external | Scrum Master | Developer | Developer | Product Manager
0.2.0 | 30 | The client may have other ideas as to what the application should be capable of. If what they want is within reason, we can add support for this feature. | Professor Mustafa pitched the idea of other types of algorithms rather than just sorting algorithms. These include Mandelbroth and Fibonaci | Scrum Master | Developer | Developer | Product Manager
0.2.1 | 40 | After the pandemic, the project had stagnated in development | Nikita held a meeting so we could evaluate where we are and what steps we'll be taking next | Team Member | Team Member | Team Member | Scrum Master
0.2.2 | 50 | We need to make a commitment to a development environment. Preferably something that would allow us to real-time test our React Native code across multiple platforms. Bonus if it allows for quick distribution. | Aleksandar introduced us to Expo, which meets all of our development and production requirements | Scrum Master | Developer | Developer | Product Manager
0.3.0 | 75 | We should create the first sorting algorithm. This will give us a good baseline for how difficult it would be to create one, and we can decide to scale back on the features if they prove to be too difficult. | Naglis implemented Merge sort. He realized that animating each sort was going to be extremely tedious and time consuming. Given the reduced development time for the project, we may end up cutting the other sorts. This successful implementation however was a strong proof of concept. | Developer | Developer | Scrum Master | Product Manager
0.4.0 | 10 | More datasets adds more variety, also adds proof for the demo that the sorting is not illegitimate (eg. prerecorded) | Naglis implemented the ability to generate new arrays and datasets | Developer | Developer | Scrum Master | Product Manager
0.4.1 | 25 | The client would like to review the product (and check our progress to see how we're doing.) This is a good time for feedback, and to ensure that the application is on track to do what is expected. | Met with Professor Mustafa. Checked in on our progress, reviewed the current demo, and scheduled a future meeting | Team Member | Team Member | Team Member | Product Manager
0.5.0 | 52 | Project requirements involved hooking up to some form of a database | Naglis integrated Firebase for account creation and login flow | Developer | Developer | Scrum Master | Product Manager
0.6.0 | 100 | We wanted our application to deploy to Android (among other platforms) | Naglis built and successfully tested the first Android build of the project | Developer | Scrum Master | Scrum Master | Product Manager
0.6.1 | 50 | Two codebases building different features need to be merged and fixed of any conflicts | Michael merged the team's development Github repo branches to main | Developer | Product Manager | Scrum Master | Team Member
0.6.2 | 100 | Final presentation due to summarize project to client | Aleksandar worked on the final product presentation for the client (Professor Mustafa) | Team Member | Developer | Team Member | Product Manager